## UAT Plan Overview
WHRD HUB — REPORTING PLATFORM
User Acceptance Testing (UAT) — Test Plan & Scenarios
Prepared by: Oliver Wainaina
DOCUMENT CONTROL
Document Title | WHRD Hub UAT Test Scenarios & Sign-off Workbook
Version | 1.0
Date | 27 June 2026
Prepared by | Oliver Wainaina
Reviewed by | [To be completed]
Approved by | [To be completed after UAT]
UAT Period | [Start Date] to [End Date]
Platform | WHRD Hub — Reporting Platform
Status | DRAFT — Pending UAT Execution
1. PURPOSE & SCOPE
This workbook defines the User Acceptance Testing (UAT) framework for the WHRD Hub Reporting Platform — a secure, anonymous incident reporting tool for Women Human Rights Defenders (WHRDs) in Kenya. The platform allows victims of Technology-Facilitated Gender-Based Violence (TFGBV) and physical GBV to report incidents, access support services, and connect with WHRD Hub defenders. This UAT covers all three user flows (Anonymous, Email/Password, Google OAuth), the admin case management flow, multilingual support, and accessibility.
2. UAT EXECUTION RULES
Individual Login Required | Each tester must access the staging platform using credentials provided by Oliver Wainaina. Shared logins are not permitted. Anonymous flow testers do not need pre-provisioned credentials.
Execute All Assigned Scenarios | Each tester must execute all scenarios assigned to their role. Skipping a scenario requires written justification.
Document All Results | For every scenario: record the Actual Result, Status (Pass/Fail/Blocked), and any Comments. Leave no row blank.
Raise Defects Immediately | Any failure must be logged in the Defect Log sheet immediately, with steps to reproduce and the URL at which the failure occurred.
No Workarounds Accepted | If a step fails, do not work around it — log it as a defect. A Pass result requires the system to behave exactly as specified in the Expected Result column.
Retest After Fix | Any defect fixed by the development team must be retested by the original tester. The retest result must be recorded in the Defect Log.
Sign-Off Required | UAT is only complete when ALL assigned scenarios are Passed (or formally deferred), and the sign-off register is completed.
UAT Environment | All testing must be conducted in the designated staging environment. Production data must not be used.
Test Data | Use fictional names, fictional locations (e.g. 'Nairobi'), and placeholder images. Do not submit real personal information.
3. DEFECT SEVERITY DEFINITIONS
🔴 CRITICAL | Platform crash, data loss, security breach, or complete failure of a core flow (submission, login, admin access). Testing cannot continue until resolved.
🟠 HIGH | Core functionality is broken but a workaround exists. Significantly impacts a user flow (e.g. form does not submit, validation missing, data not saved).
🟡 MEDIUM | Non-core functionality affected. System behaviour differs from specification but the primary flow can be completed (e.g. wrong label, missing translation, chart not rendering).
🟢 LOW | Minor UI issue, copy error, or cosmetic defect. Does not affect system function (e.g. misaligned button, wrong colour, spelling error).
4. TEST SCOPE — MODULES & SCENARIO COUNT
Module ID | Module Name & Scenario Count
MOD-01 | System Access & Authentication — 5 scenarios
MOD-02 | Anonymous Reporting Flow — 8 scenarios
MOD-03 | Report Form — Fields, Validation & TFGBV — 10 scenarios
MOD-04 | Account Generation, Onboarding & Role Selection — 5 scenarios
MOD-05 | Email & Password User Flow — 6 scenarios
MOD-06 | Google OAuth Flow — 5 scenarios
MOD-07 | Reporter Dashboard — 5 scenarios
MOD-08 | Admin — Reports & Case Management — 6 scenarios
MOD-09 | Admin — Fact-Checking — 5 scenarios
MOD-10 | Admin — Analytics & Map Interface — 6 scenarios
MOD-11 | Settings & Language Switcher — 6 scenarios
MOD-12 | Multilingual Testing (EN/SW/FR/PT/DE/AR) — 8 scenarios
MOD-13 | Accessibility — Keyboard, Contrast & Screen Reader — 7 scenarios
TOTAL | 72 Test Scenarios
⚠ STAGING ENVIRONMENT — GOOGLE OAUTH: Each tester's Gmail address must be added to the Supabase allowlist by Oliver Wainaina before the Google OAuth flow can be tested. Send your Gmail address to oliverwai9na@gmail.com with subject 'WHRD Hub UAT Access Request' and await confirmation before beginning MOD-06. Email/Password and Anonymous flows require no pre-registration.

## Test Scenarios
WHRD HUB — UAT TEST SCENARIOS
Test ID | Module | Scenario Title | Test Type | Pre-Conditions | Test Data Required | Test Steps (numbered) | Expected Result | Actual Result (Tester fills in) | Status (Pass/Fail/Blocked) | Defect Ref | Tester Name | Date Tested | Comments / Observations
MOD-01 — System Access & Authentication
TC-001 | MOD-01 System Access | Landing Page Loads and Renders Correctly | Positive | Staging URL provided by Oliver Wainaina. Device: Desktop Chrome (latest). | URL: [staging URL as shared by Oliver] Browser: Chrome 120+ | 1. Open the staging URL in a Chrome browser. 2. Allow the page to fully load (wait for network idle). 3. Observe all sections of the landing page. 4. Open browser developer console (F12) and check for errors. | Landing page loads within 5 seconds. All sections visible: navigation bar with WHRD Hub logo, 'Report now' CTA button, hero section with headline, safety banner, 'How it works' section, 'What you can report' section, statistics strip, CTA section, emergency contacts strip, and footer. Zero JavaScript errors in the browser console. |  | Not Tested
TC-002 | MOD-01 System Access | Unauthenticated User Cannot Access Dashboard | Validation | User is not signed in. Browser has no active session cookie. | No credentials required. Browser with cleared cookies. | 1. Ensure you are not signed in (clear cookies if needed). 2. Manually type the dashboard URL ([staging URL]/dashboard) directly into the address bar. 3. Press Enter. 4. Observe where the page redirects. | User is immediately redirected away from /dashboard. The system returns the user to the login page (/auth/login) or the landing page. The dashboard content is not displayed to an unauthenticated user under any circumstances. |  | Not Tested
TC-003 | MOD-01 System Access | Sign In with Email and Password — Successful | Positive | A confirmed email/password account exists in the staging system. Onboarding has been completed on this account. | Email: [your registered test email] Password: [your test password — minimum 8 characters] | 1. Navigate to /auth/login. 2. Enter your registered email address in the 'Username or Email' field. 3. Enter your password in the Password field. 4. Click 'Log In'. 5. Observe the redirect destination. | Login succeeds. The 'Log In' button shows a loading state ('Logging in…') while the request is processed. User is redirected to /dashboard within 3 seconds. The dashboard displays the user's name or email, their report count, and the navigation menu. |  | Not Tested
TC-004 | MOD-01 System Access | Login Failure — Incorrect Password | Negative | A confirmed email/password account exists in the staging system. | Email: [your registered test email] Password: WrongPassword99 (intentionally incorrect) | 1. Navigate to /auth/login. 2. Enter your registered email address. 3. Enter 'WrongPassword99' as the password (incorrect). 4. Click 'Log In'. 5. Observe the response. | The system displays a red inline error message: 'Incorrect username/email or password.' The page does not redirect. The password field is cleared. The user remains on the login page. No account lockout on first attempt. |  | Not Tested
TC-005 | MOD-01 System Access | Sign Out — Session Terminated | Positive | User is signed in to any account type (Email, Google, or Anonymous). User is on the /dashboard page. | Any active signed-in session. | 1. From the dashboard, locate and click the 'Sign out' button or link. 2. Observe the redirect. 3. After sign-out, manually type [staging URL]/dashboard in the address bar. 4. Press Enter. | Step 2: User is redirected to the landing page or /auth/login. Session is terminated. Step 4: User is redirected away from /dashboard — the dashboard content is not accessible. Browser cookies for the session are cleared. |  | Not Tested
MOD-02 — Anonymous Reporting Flow
TC-006 | MOD-02 Anonymous Flow | 'Report Now' CTA Navigates to Report Form | Positive | User is not signed in. Landing page is loaded. | No credentials required. | 1. On the landing page, locate the purple 'Report now' button in the navigation bar (top right). 2. Click the button. 3. Observe the navigation and page content. | User is navigated to /report. The report form page loads with a page heading and all six sections visible: (1) About this report, (2) What happened, (3) Who did this, (4) Online evidence [conditional], (5) How can we help, (6) Your private access. No login prompt is shown. |  | Not Tested
TC-007 | MOD-02 Anonymous Flow | Submit Report with No Required Fields — Validation Errors | Validation | User is on /report. User is not signed in. No fields have been filled. | No data — testing empty submission. | 1. Navigate to /report. 2. Scroll to the bottom of the page without filling any fields. 3. Click 'Submit report securely'. 4. Scroll back up and observe the form. | The page does not navigate away. Three distinct inline validation errors appear in red directly beneath the relevant fields: • Under 'Where did the violence happen?': 'Please select where the violence happened.' • Under 'Tell us what happened': 'Please describe what happened (0/20 minimum characters).' • Under 'County / Region': 'Please select a county or region.' The submit button does not trigger any loading state. |  | Not Tested
TC-008 | MOD-02 Anonymous Flow | Violence Type = Online — Evidence Section Appears | Positive | User is on /report. User has not yet selected a violence type. | No specific test data required. | 1. On /report, locate the 'Where did the violence happen?' section. 2. Click the 'Online' pill button. 3. Observe the form below the 'Who did this?' section. | The 'Online' pill turns purple and displays a white check icon. A new card titled 'Online evidence' appears below the 'Who did this?' section, containing three fields: Platform (dropdown), Link to the content (URL input), and Upload screenshots (file picker). This section is not visible when 'Physical / In person' is selected. |  | Not Tested
TC-009 | MOD-02 Anonymous Flow | Description Character Counter and Minimum Length | Validation | User is on /report. | Input: type exactly 10 characters in the description field, e.g. 'Test input' | 1. Click into the 'Tell us what happened' textarea. 2. Type exactly 10 characters (e.g. 'Test input'). 3. Observe the hint text below the textarea. 4. Continue typing until 20 characters are reached. 5. Observe the hint text again. | Step 3: A grey hint below the textarea reads '10/20 min', indicating 10 of the required 20 minimum characters have been entered. Step 5: Once 20 characters are reached, the hint disappears entirely. The field is now considered valid. |  | Not Tested
TC-010 | MOD-02 Anonymous Flow | Successful Anonymous Report Submission and Account Generation | Positive | User is not signed in. User is on /report. | Violence type: Online Description: 'Test incident submitted during WHRD Hub UAT exercise in Nairobi county.' (71 chars) County: Nairobi Password: TestPass2026 (All other fields optional — leave blank) | 1. On /report, click the 'Online' pill for Violence type. 2. In 'Tell us what happened', enter: 'Test incident submitted during WHRD Hub UAT exercise in Nairobi county.' 3. Select 'Nairobi' from the County dropdown. 4. Scroll to 'Your private access' section. 5. Enter password: TestPass2026. 6. Click 'Submit report securely'. 7. Observe the button state and subsequent navigation. | Step 6-7: The button label changes to 'Submitting…' with a spinning loader icon. After 2–4 seconds, the user is navigated to /report/success. The success page displays: a green check icon, 'Report received' heading, a list of next steps, and a notice reading 'You are already signed in'. The user is automatically logged into their newly created anonymous account — no separate login step is required. |  | Not Tested
TC-011 | MOD-02 Anonymous Flow | Success Page — 'Go to Your Dashboard' Button | Positive | User has just completed TC-010 successfully. User is on /report/success. User is automatically signed in. | No additional data required. | 1. On /report/success, locate the 'Go to your dashboard' button. 2. Click the button. 3. Observe the navigation and dashboard content. | User is navigated directly to /dashboard. The dashboard loads without displaying a login form. The user is already authenticated. The dashboard shows: one report in the report list (the report just submitted), summary cards showing '1 Report Submitted', and — because this is an anonymous account — a 'Your login credentials' card showing the auto-generated username and email. |  | Not Tested
TC-012 | MOD-02 Anonymous Flow | Anonymous Credentials Displayed on Dashboard | Positive | User has completed TC-010 and TC-011. User is on /dashboard as an anonymous user. | Note the username and email shown on the credentials card for use in TC-013. | 1. On /dashboard, locate the 'Your login credentials' card. 2. Note the auto-generated username (e.g. brave-shield-k4x2). 3. Note the virtual email (e.g. brave-shield-k4x2@whrdhub.local). 4. Click the copy icon/button next to the email address. 5. Paste the copied value into a text editor to verify it copied correctly. | A credentials card is visible only for anonymous users. It displays a system-generated username in the format [adjective]-[noun]-[code] and a corresponding virtual email in the format [username]@whrdhub.local. The copy button successfully copies the email to the clipboard. Authenticated (non-anonymous) users do not see this card. |  | Not Tested
TC-013 | MOD-02 Anonymous Flow | Anonymous User Sign Out and Sign Back In Using Username | Positive | User has completed TC-012. User has noted their auto-generated username and the password chosen in TC-010 (TestPass2026). | Username: [noted from TC-012 credentials card] Password: TestPass2026 | 1. From the dashboard, click 'Sign out'. 2. Navigate to /auth/login. 3. In the 'Username or Email' field, enter only the username (e.g. brave-shield-k4x2) — not the full email. 4. Enter password: TestPass2026. 5. Click 'Log In'. | Sign-in succeeds. User is redirected to /dashboard (if onboarding is already complete) or /onboarding (if not yet completed). The report submitted in TC-010 is visible in the dashboard report list. The credentials card is visible showing the same username and email as noted in TC-012. |  | Not Tested
MOD-03 — Report Form — Fields, Validation & TFGBV
TC-014 | MOD-03 Report Form | Reporting For — 'A Child' Selection | Positive | User is on /report (signed in or anonymous). | No specific test data. | 1. On /report, locate the 'Who are you reporting for?' section. 2. Click the 'A child' pill button. 3. Observe the pill state. 4. Select another option (e.g. 'Myself'). 5. Observe the previous pill state. | Step 2-3: The 'A child' pill turns purple with a check icon. Only one pill can be active at a time — all others revert to unselected state. Step 4-5: 'Myself' becomes selected, 'A child' reverts to unselected. The form does not display any child-specific fields to the reporter (the child-protection flag is internal to the admin system). |  | Not Tested
TC-015 | MOD-03 Report Form | Perpetrator Type Selection Reveals Detail Field | Positive | User is on /report. Violence type has been selected. | Perpetrator type to select: 'Partner / Spouse' Detail text: 'John Doe, self-employed, Westlands' | 1. Scroll to the 'Who did this?' section. 2. Click the 'Partner / Spouse' pill. 3. Observe the form below the pills. 4. In the detail input that appears, type: 'John Doe, self-employed, Westlands'. 5. Click the 'Partner / Spouse' pill again to deselect it. 6. Observe the detail input. | Step 2-3: The 'Partner / Spouse' pill turns purple with a check icon. A text input field appears below the pills labelled 'Any details? (optional)'. Step 4: The text is accepted without restriction. Step 5-6: The pill deselects and the detail text input disappears. This confirms the field is fully conditional on perpetrator selection. |  | Not Tested
TC-016 | MOD-03 Report Form | Multi-Select Support Type Pills | Positive | User is on /report. Scroll to 'How can we help?' section. | Support types to select: Legal support, Counselling, Other Other text: 'Temporary housing assistance' | 1. In the 'How can we help?' section, click 'Legal support'. 2. Click 'Counselling'. 3. Click 'Other'. 4. In the text area that appears, enter: 'Temporary housing assistance'. 5. Click 'Counselling' a second time to deselect it. 6. Observe which pills remain selected. | Steps 1-3: Each pill independently turns purple with a check icon. Multiple pills can be selected simultaneously — this is not a single-select control. Step 3-4: Selecting 'Other' reveals a freetext textarea immediately below the pills. Step 5-6: 'Counselling' deselects and reverts to default styling. 'Legal support' and 'Other' remain selected. |  | Not Tested
TC-017 | MOD-03 Report Form | Urgency Selection — Immediate Danger Turns Red | Positive | User is on /report. Scroll to urgency buttons in 'How can we help?' section. | No specific data required. | 1. In the 'How can we help?' section, locate the three urgency buttons. 2. Click 'I am in danger right now' (the top button). 3. Observe the button colour. 4. Click 'No rush, documenting' (the bottom button). 5. Observe both buttons. | Step 2-3: The 'I am in danger right now' button turns red with white text, indicating critical urgency. Step 4-5: 'No rush, documenting' becomes selected (default styling). The 'I am in danger right now' button reverts to its default state. Only one urgency level can be selected at a time. |  | Not Tested
TC-018 | MOD-03 Report Form | Consent to Contact — Reveals Contact Fields | Positive | User is on /report. Scroll to consent checkbox in 'How can we help?' section. | Contact method: WhatsApp Contact value: +254 7XX XXX XXX (fictional number) | 1. Locate the checkbox 'I am okay with being contacted by a WHRD Hub defender'. 2. Check the checkbox. 3. Observe the form below the checkbox. 4. In the contact method dropdown, select 'WhatsApp'. 5. In the contact detail field, enter: +254 700 000 000. 6. Uncheck the checkbox. 7. Observe the contact fields. | Step 2-3: Two fields appear below the checkbox: a dropdown for 'Preferred method' (options: Phone call, WhatsApp, Email, SMS) and a text input for 'Phone number or email'. Step 4-5: Fields accept input normally. Step 6-7: Both contact fields disappear. Unchecking consent hides the contact fields entirely. |  | Not Tested
TC-019 | MOD-03 Report Form | TFGBV Platform and Link Fields — Online Evidence Section | Positive | User is on /report. Violence type is set to 'Online' or 'Both'. | Platform: WhatsApp Link: https://wa.me/invalid-test-link | 1. Ensure 'Online' is selected as the violence type. 2. Scroll to the 'Online evidence' section. 3. In the Platform dropdown, select 'WhatsApp'. 4. In the Link field, enter: https://wa.me/invalid-test-link. 5. Observe the fields and their labels. | The 'Online evidence' section is visible. The Platform dropdown accepts 'WhatsApp' as a selection. The Link field accepts URL input. Both fields are optional — no validation error is triggered if left blank. The section title and field labels are correct (testing English language by default). |  | Not Tested
TC-020 | MOD-03 Report Form | Screenshot Upload — File Picker Accepts Images | Positive | User is on /report. Violence type is set to 'Online'. User has a small JPEG image (< 5 MB) available on their device. | Test file: Any JPEG image under 5 MB (a screenshot, a generic image — not an actual incident image). | 1. Scroll to the 'Online evidence' section. 2. Click 'Choose files (JPEG, PNG, PDF — max 5 MB each)'. 3. In the file picker, select a small JPEG image. 4. Observe the file list below the picker. 5. Click the × (remove) button next to the uploaded file. | Step 3-4: The file is accepted and listed below the picker with its filename and file size in KB. A remove button (×) is visible next to each file. Step 5: Clicking × removes the file from the list. The picker accepts up to 10 files simultaneously; attempting to add an 11th triggers an error toast: 'Maximum 10 files'. |  | Not Tested
TC-021 | MOD-03 Report Form | Password Field — Minimum Length Validation | Negative | User is not signed in. User is on /report. Required fields (violence type, description, county) are already filled. | Password attempt 1: UAT1 (4 characters — too short) Password attempt 2: UATTest2026 (11 characters — valid) | 1. Scroll to the 'Your private access' section. 2. In the password field, enter: UAT1 (4 characters). 3. Click 'Submit report securely'. 4. Observe the password field. 5. Clear the password field and enter: UATTest2026 (11 characters). 6. Observe the error state. | Step 3-4: A red error message appears directly below the password field: 'Password must be at least 8 characters.' The form does not submit. A red border appears on the password field. Step 5-6: As soon as 8 characters are entered, the red error and red border disappear. The field returns to its default state. |  | Not Tested
TC-022 | MOD-03 Report Form | GPS Location Capture Notice | Positive | User is on /report. Browser location permissions have been granted (or will be requested). | Allow location permission when prompted by the browser. | 1. Navigate to /report. 2. When the browser displays a location permission prompt, click 'Allow'. 3. Scroll to the 'What happened' section and observe beneath the 'Is ongoing' checkbox. | After location permission is granted, a green notice appears: 'GPS noted for anonymised map visualisation only.' This confirms the browser geolocation was captured. If permission is denied, this notice does not appear and no error is shown to the user — geolocation is optional. |  | Not Tested
TC-023 | MOD-03 Report Form | Authenticated User — No Password Field on Report Form | Validation | User is signed in with an Email/Password or Google account. Onboarding is complete. | Any signed-in session. | 1. While signed in, navigate to /report. 2. Scroll to the 'Your private access' section at the bottom of the form. | The password creation field is NOT shown. Instead, a green banner displays: a shield icon, 'Signed in' label, and the user's email address with a copy button. No credentials section, no password warning, and no auto-username notice are shown to signed-in users. |  | Not Tested
MOD-04 — Account Generation, Onboarding & Role Selection
TC-024 | MOD-04 Onboarding | New User Redirected to Onboarding Before Dashboard | Validation | A brand new account has been created (either via TC-010 anonymous submission, email sign-up, or first Google login). Onboarding has NOT yet been completed on this account. | New account credentials (from TC-010, or a fresh sign-up). | 1. Sign in with a newly created account. 2. Immediately after sign-in, observe the redirect destination. 3. Alternatively, navigate directly to /dashboard. | The user is redirected to /onboarding before being allowed to view /dashboard. The onboarding page loads with: a role selection section (Admin / WHRD cards), a Terms & Conditions section with accordion panels, and a 'Proceed to dashboard' button that is initially disabled. |  | Not Tested
TC-025 | MOD-04 Onboarding | Role Selection — Cannot Proceed Without Selecting Role | Validation | User is on /onboarding. No role has been selected yet. | No test data required. | 1. On /onboarding, do NOT click any role card. 2. Attempt to click the 'Proceed to dashboard' (or equivalent) button. | The 'Proceed to dashboard' button remains disabled (greyed out) and cannot be clicked while no role is selected. No error message is required — the button's disabled state communicates the requirement. The user must select a role card before proceeding. |  | Not Tested
TC-026 | MOD-04 Onboarding | Terms & Conditions Accordion — Expand and Read | Positive | User is on /onboarding. | No test data required. | 1. On /onboarding, locate the Terms & Conditions section. 2. Click the first accordion panel header to expand it. 3. Read the content. 4. Click a second accordion panel to expand it. 5. Attempt to proceed without checking the acceptance checkbox. | Step 2-4: Each accordion panel expands to reveal policy text. Multiple accordions can be open simultaneously, or only one — note the behaviour. Step 5: The 'Proceed to dashboard' button remains disabled until the acceptance checkbox is checked. |  | Not Tested
TC-027 | MOD-04 Onboarding | Complete Onboarding — Role + T&C + Proceed | Positive | User is on /onboarding. User has not yet completed onboarding. | Role to select: WHRD | 1. On /onboarding, click the 'WHRD' role card. 2. Expand and read the Terms & Conditions accordions. 3. Check the 'I accept the terms and conditions' checkbox. 4. Click 'Proceed to dashboard'. | Step 1: The 'WHRD' card highlights with a selected state (border, background change, or check icon). Step 3: The 'Proceed to dashboard' button becomes active/enabled. Step 4: User is navigated to /dashboard. Onboarding completion is saved — subsequent sign-ins on this account go directly to /dashboard without redirecting to /onboarding. |  | Not Tested
TC-028 | MOD-04 Onboarding | Onboarding Not Re-Triggered on Subsequent Login | Validation | User has completed TC-027 successfully. User is on /dashboard. | Same account used in TC-027. | 1. From /dashboard, click 'Sign out'. 2. Sign back in with the same account credentials. 3. Observe the redirect destination after login. | After sign-in, the user is navigated directly to /dashboard. The /onboarding page is NOT shown. The role and T&C acceptance from TC-027 are persisted. This confirms onboarding completion is correctly stored and the gate is not re-triggered on subsequent sessions. |  | Not Tested
MOD-05 — Email & Password User Flow
TC-029 | MOD-05 Email Flow | New Account Sign-Up with Email and Password | Positive | No existing account with the test email address. | Email: [your personal test email address] Password: UATEmail2026 (Use an email you have access to — confirmation email required) | 1. Navigate to /auth/sign-up. 2. Enter your test email address. 3. Enter password: UATEmail2026. 4. Click 'Sign up'. 5. Check your email inbox. | Step 4: A success message is displayed on screen confirming a confirmation email has been sent. Step 5: A confirmation email arrives in your inbox within 2 minutes. Check the spam/junk folder if not received. The email contains a confirmation link. |  | Not Tested
TC-030 | MOD-05 Email Flow | Email Confirmation Link — Account Activated | Positive | TC-029 has been completed and a confirmation email received. | Confirmation link from the email received in TC-029. | 1. Open the confirmation email from WHRD Hub. 2. Click the confirmation link in the email. 3. Observe the page that opens. | Clicking the confirmation link opens the platform and confirms the account. The user is redirected to /onboarding (first login) or /dashboard (if already onboarded). The account is now active and can be used to sign in with email and password. |  | Not Tested
TC-031 | MOD-05 Email Flow | Duplicate Email Registration Blocked | Negative | The email address from TC-029 is already registered. | Email: same email used in TC-029 (already registered) | 1. Navigate to /auth/sign-up. 2. Enter the same email address used in TC-029. 3. Enter any password. 4. Click 'Sign up'. 5. Observe the response. | The system displays an error message such as 'User already registered' or equivalent. A second account is not created for the same email address. The user is presented with options to sign in or reset their password instead. |  | Not Tested
TC-032 | MOD-05 Email Flow | Email User — Submit Report as Authenticated User | Positive | Email/password account confirmed and signed in. Onboarding completed. | Violence type: Physical / In person Description: 'UAT test report submitted by authenticated email user during WHRD Hub UAT exercise.' (74 chars) County: Mombasa | 1. Ensure you are signed in with your email account. 2. Navigate to /report. 3. Select 'Physical / In person' as violence type. 4. Enter the description above. 5. Select 'Mombasa' from the County dropdown. 6. Scroll to 'Your private access' — note what you see. 7. Click 'Submit report securely'. | Step 6: The 'Your private access' section shows a green 'Signed in' banner with the user's email address — no password field is shown. Step 7: The submission succeeds. A toast notification appears: 'Report submitted. Thank you for your courage.' The user is redirected to /dashboard where the new report appears in the report list. |  | Not Tested
TC-033 | MOD-05 Email Flow | Report Appears on Dashboard After Submission | Positive | TC-032 completed successfully. User is on /dashboard. | No additional data required. | 1. On /dashboard after TC-032, locate the report list section. 2. Find the report submitted in TC-032. 3. Observe the report entry details. | The report submitted in TC-032 is listed in the dashboard report list. The entry shows: the incident type chip ('Physical / In person'), the county ('Mombasa'), the submission date (today's date), and a status badge ('Pending review' or equivalent). The 'Reports Submitted' counter on the dashboard increments to reflect the new submission. |  | Not Tested
TC-034 | MOD-05 Email Flow | Forgot Password Flow | Positive | Email/password account exists and is confirmed. | Email: [your registered test email] | 1. Navigate to /auth/login. 2. Click the 'Forgot password?' link next to the password field. 3. Enter your registered email address. 4. Click the submit/send button. 5. Check your email inbox for a reset link. | Step 3-4: A confirmation message is shown: password reset instructions sent to the email address. Step 5: A password reset email is received within 2 minutes. Note: This tests that the forgot password flow is functional. Full password reset execution is not required for this UAT — confirm the email is received and the link is valid. |  | Not Tested
MOD-06 — Google OAuth Flow
⚠ PREREQUISITE FOR MOD-06: Your Gmail address must be added to the Supabase staging allowlist by Oliver Wainaina before any test in this module can be executed. If access has not been confirmed, mark all MOD-06 scenarios as 'Blocked' and log a prerequisite note in the Comments column.
TC-035 | MOD-06 Google OAuth | Sign In with Google — Account Picker Appears | Positive | Gmail address has been added to Supabase allowlist by Oliver. User is on /auth/login and NOT already signed in. | Gmail account: [your Gmail address, pre-registered with Oliver] | 1. Navigate to /auth/login. 2. Click 'Continue with Google'. 3. Observe the button state. 4. Observe the Google account picker that appears. | Step 3: The 'Continue with Google' button changes to 'Redirecting…' and is disabled. Step 4: The browser opens Google's OAuth consent screen or account picker. The Google flow is initiated from the WHRD Hub staging domain. |  | Not Tested
TC-036 | MOD-06 Google OAuth | First-Time Google Sign-In — Redirected to Onboarding | Positive | TC-035 Google account has never previously signed in to WHRD Hub staging. Google account picker is open from TC-035. | Gmail: [your Gmail — first time use] | 1. In the Google account picker, select your Gmail account. 2. Grant any requested permissions. 3. Observe the redirect destination after Google returns you to the platform. | After Google authentication, the user is redirected to /onboarding. The onboarding page loads with role selection and T&C acceptance. The user's Google display name or email may be shown. The user is NOT taken to /dashboard until onboarding is complete. |  | Not Tested
TC-037 | MOD-06 Google OAuth | Google User Completes Onboarding and Reaches Dashboard | Positive | TC-036 completed — user is on /onboarding after first Google sign-in. | Role to select: WHRD | 1. On /onboarding, select the 'WHRD' role card. 2. Check the T&C acceptance checkbox. 3. Click 'Proceed to dashboard'. | User is navigated to /dashboard. The dashboard displays the user's Google email in the top-right or in the account section. The 'Your login credentials' anonymous card is NOT shown — this is a Google authenticated user. Report count is zero (no reports yet). |  | Not Tested
TC-038 | MOD-06 Google OAuth | Returning Google User — Bypasses Onboarding | Positive | TC-037 completed successfully. User has signed out. | Same Gmail used in TC-035. | 1. Sign out from the dashboard. 2. Navigate to /auth/login. 3. Click 'Continue with Google'. 4. Select the same Gmail account in the account picker. | After Google authentication, the user is redirected directly to /dashboard. The /onboarding page is NOT shown. Onboarding completion is persisted from TC-037. |  | Not Tested
TC-039 | MOD-06 Google OAuth | Google User Submits Report as Authenticated | Positive | Google account signed in and onboarding complete. | Violence type: Both Description: 'UAT test report from a Google authenticated user on the WHRD Hub staging platform.' (78 chars) County: Kisumu | 1. While signed in with Google, navigate to /report. 2. Select 'Both' as violence type. 3. Enter the description above. 4. Select 'Kisumu' from the County dropdown. 5. Scroll to 'Your private access' and note the content. 6. Click 'Submit report securely'. | Step 5: Green 'Signed in' banner showing the Gmail address. No password field. Step 6: Report submits successfully. Toast: 'Report submitted. Thank you for your courage.' Redirected to /dashboard. New report visible in the list with type chips for both Online and Physical, county Kisumu. |  | Not Tested
MOD-07 — Reporter Dashboard
TC-040 | MOD-07 Dashboard | Dashboard Summary Cards Show Correct Counts | Positive | User is signed in with an account that has at least one submitted report. | Account with reports submitted during MOD-02, MOD-05, or MOD-06 testing. | 1. Navigate to /dashboard. 2. Observe the summary cards at the top of the page. 3. Note the count shown on each card: 'Reports Submitted', 'Under Review', 'Resolved'. | The 'Reports Submitted' card shows the total number of reports submitted from this account. 'Under Review' and 'Resolved' counts reflect the current admin-updated status of those reports. Counts are accurate and match the number of reports visible in the report list below. |  | Not Tested
TC-041 | MOD-07 Dashboard | Report List — Status Badges Reflect Admin Updates | Positive | An admin has updated at least one report to 'Under Review' status (can be done during MOD-09 admin testing). | A report whose status has been changed to 'Under Review' by the admin. | 1. On /dashboard, scroll to the report list. 2. Locate the report whose status was changed during admin testing. 3. Observe the status badge on that report. | The report entry shows an 'Under Review' status badge. The badge colour and label match the admin-set status. This confirms that reporter dashboard status reflects admin changes in real time (or on refresh). |  | Not Tested
TC-042 | MOD-07 Dashboard | Empty State — No Reports Displays CTA | Positive | User is signed in with a brand new account that has submitted zero reports. (Create a fresh account for this test.) | Fresh account with no reports. | 1. Sign in with a brand new account that has no reports. 2. Complete onboarding. 3. Navigate to /dashboard. 4. Observe the report list area. | In place of a report list, an empty state is shown with a friendly message (e.g. 'No reports yet') and a 'Make a report' call-to-action button. Clicking the CTA navigates to /report. |  | Not Tested
TC-043 | MOD-07 Dashboard | Settings Link — Navigates to /settings | Positive | User is signed in. User is on /dashboard. | No specific data required. | 1. On /dashboard, locate the Settings link or button (in the navigation or dashboard body). 2. Click it. | User is navigated to /settings. The settings page loads with a language selection grid showing all 6 language options. No login prompt is shown. |  | Not Tested
TC-044 | MOD-07 Dashboard | Dashboard Not Accessible Without Sign-In | Validation | User has signed out or has no active session. | No credentials. | 1. Sign out if currently signed in. 2. Type /dashboard directly into the browser address bar. 3. Press Enter. | User is immediately redirected away from /dashboard. The redirect destination is either /auth/login or the landing page. The dashboard content (reports, stats, credentials) is not rendered or visible at any point. |  | Not Tested
MOD-08 — Admin — Reports & Case Management
PREREQUISITE: Admin credentials must be provided by Oliver Wainaina. Regular WHRD users do not have admin access. Attempting to access /admin as a non-admin results in a redirect.
TC-045 | MOD-08 Admin Reports | Admin Dashboard Loads with Statistics | Positive | Admin account credentials received from Oliver Wainaina. User is signed in as admin. | Admin credentials: [provided by Oliver] | 1. Sign in using admin credentials. 2. Navigate to /admin. 3. Observe the page content. | The admin dashboard loads successfully. Summary statistics are visible: total reports, reports under review, resolved reports, and any other key metrics. An admin-specific navigation bar is shown (e.g. Reports, Analytics, Map). |  | Not Tested
TC-046 | MOD-08 Admin Reports | Non-Admin User Blocked from Admin Panel | Validation | A non-admin (WHRD) user account is signed in. | Non-admin account (e.g. account created during MOD-05 or MOD-06). | 1. Sign in with a non-admin account. 2. Manually navigate to /admin by typing it into the address bar. 3. Observe the result. | The system does not display the admin panel. The user is redirected to /dashboard or a 'Not authorised' / '403 Forbidden' page. The admin report list, fact-check form, and analytics are not accessible. |  | Not Tested
TC-047 | MOD-08 Admin Reports | Admin Reports List — All Submissions Visible | Positive | Admin is signed in. At least 2 reports have been submitted by different accounts during earlier test modules. | Reports submitted during MOD-02 (TC-010), MOD-05 (TC-032), MOD-06 (TC-039). | 1. As admin, navigate to /admin/reports. 2. Observe the list of reports. 3. Confirm reports from multiple user types are visible. | A list or table of all reports submitted to the platform is shown. Reports from anonymous, email, and Google users all appear in the same admin list. Each report entry shows key fields: report reference/ID, reporter type, county, incident type, urgency, status, and submission date. |  | Not Tested
TC-048 | MOD-08 Admin Reports | Open Individual Report — All Fields Visible | Positive | Admin is signed in. Admin is on /admin/reports. | Any report from the list (preferably TC-010 — the anonymous report with description, county, and platform set). | 1. On /admin/reports, click on the report submitted in TC-010. 2. Observe the report detail page at /admin/reports/[id]. | The full report detail page loads. Visible fields include: description, violence type, county, perpetrator type (if set), urgency, support needed, is_ongoing flag, platform (if online), and reporter information. For anonymous reporters, a badge reads 'Anonymous' and the auto-generated username is shown. No 404 error is returned. |  | Not Tested
TC-049 | MOD-08 Admin Reports | Anonymous Reporter — No Real Email Exposed in Admin View | Validation | Admin is viewing the detail page for a report submitted by an anonymous user (from TC-010). | Report from TC-010 (anonymous submission). | 1. Open the detail page for the anonymous report from TC-010. 2. Inspect the reporter information section carefully. 3. Look for any display of a real email address, real name, or other PII. | The reporter section shows: 'Anonymous' badge, the auto-generated username (e.g. brave-shield-k4x2), and the virtual email (e.g. brave-shield-k4x2@whrdhub.local). No real name, real email, phone number, or IP address is displayed. This confirms PII protection for anonymous users. |  | Not Tested
TC-050 | MOD-08 Admin Reports | Admin Submits a Report on Behalf of a Survivor | Positive | Admin is signed in. Admin is acting as an intake officer for an in-person survivor interview. | Violence type: Physical / In person Description: 'In-person intake: survivor reported repeated harassment by supervisor at place of work. Incident ongoing. Name withheld at request of survivor.' County: Nairobi Urgency: This week, help soon | 1. As admin, navigate to /report. 2. Fill in: Violence type = Physical / In person. 3. Enter the description above. 4. County = Nairobi. 5. Urgency = 'This week, help soon'. 6. Observe the 'Your private access' section. 7. Click 'Submit report securely'. | Step 6: Green 'Signed in' banner shows admin's email — no password field. Step 7: Report submits successfully. Toast notification appears. Admin is redirected to /dashboard. The report is also visible in /admin/reports with the admin's account as reporter. This flow supports in-person intake. |  | Not Tested
MOD-09 — Admin — Fact-Checking & Case Status
TC-051 | MOD-09 Fact-Checking | Fact-Check Form Visible on Individual Report Page | Positive | Admin is signed in. Admin is viewing a report detail page at /admin/reports/[id]. | Any report from TC-047 list. | 1. Open any individual report at /admin/reports/[id]. 2. Scroll through the page to locate the fact-check or case management section. | A fact-check/case management form is visible on the report detail page. It contains at minimum: a status dropdown (options including Pending, Under Review, Fact-Checked, Resolved, Rejected), an admin notes textarea, and a Save/Update button. |  | Not Tested
TC-052 | MOD-09 Fact-Checking | Update Case Status to 'Under Review' | Positive | Admin is on the detail page of a report with current status 'Pending'. | Report: TC-010 (anonymous submission) New status: Under Review Admin note: 'Case reviewed during WHRD Hub UAT exercise — initial intake complete.' | 1. On the report detail page, open the status dropdown. 2. Select 'Under Review'. 3. In the admin notes field, enter: 'Case reviewed during WHRD Hub UAT exercise — initial intake complete.' 4. Click 'Save' (or equivalent update button). 5. Observe the confirmation and the status display. | Step 4-5: The status is updated successfully. A success indicator (toast, inline message, or page reload with updated status) confirms the save. The report detail page now shows 'Under Review' as the current status. When the reporter (anonymous account from TC-013) views their dashboard, their report's status badge also reads 'Under Review'. |  | Not Tested
TC-053 | MOD-09 Fact-Checking | Update Case Status to 'Resolved' | Positive | Admin is on the detail page of a report. Status may be 'Under Review' from TC-052. | New status: Resolved Admin note: 'Case resolved during UAT — referral to legal support service completed.' | 1. On the report detail page, change the status dropdown to 'Resolved'. 2. Update the admin notes field with the note above. 3. Click 'Save'. 4. Navigate to the reporter's dashboard (sign in as the reporter in a separate browser tab). | Step 3: Save succeeds with confirmation. Step 4: The reporter's dashboard now shows the report status as 'Resolved'. The 'Resolved' counter on the reporter's dashboard increments by one. The admin's overall resolved count in /admin also increments. |  | Not Tested
TC-054 | MOD-09 Fact-Checking | Admin Notes Persist After Save and Page Refresh | Validation | Admin is on the detail page of a report. Admin notes have been saved in TC-052. | Report from TC-010 with notes entered in TC-052. | 1. On the report detail page where notes were saved in TC-052, observe the admin notes field. 2. Hard-refresh the page (Ctrl + Shift + R or Cmd + Shift + R). 3. Re-open the same report. 4. Observe the admin notes field. | After a page refresh and re-opening the report, the admin note entered in TC-052 ('Case reviewed during WHRD Hub UAT exercise — initial intake complete.') is still present in the admin notes field. Notes are persisted to the database, not stored only in browser session. |  | Not Tested
TC-055 | MOD-09 Fact-Checking | Reporter Type Indicator — Anonymous vs Authenticated | Validation | Admin has access to reports from both anonymous and authenticated users in /admin/reports. | Report from TC-010 (anonymous) and report from TC-032 (email user). | 1. Open the report from TC-010 (anonymous user) and note the reporter info section. 2. Open the report from TC-032 (email user) and note the reporter info section. 3. Compare the two. | TC-010 report: Reporter section shows 'Anonymous' badge, auto-generated username, virtual email. TC-032 report: Reporter section shows the real email address of the authenticated user. The distinction between anonymous and authenticated reporters is clearly and correctly indicated. |  | Not Tested
MOD-10 — Admin — Analytics & Map Interface
TC-056 | MOD-10 Analytics | Analytics Page Loads with Charts | Positive | Admin is signed in. At least 3 reports with different counties, types, and urgency levels have been submitted during earlier testing. | Reports from TC-010 (Nairobi, Online), TC-032 (Mombasa, Physical), TC-039 (Kisumu, Both), TC-050 (Nairobi, Physical). | 1. As admin, navigate to /admin/analytics. 2. Allow all charts to fully load. 3. Observe each chart type on the page. | The analytics page loads without errors. Charts or visualisations are visible, potentially including: reports by county, reports by violence type, reports over time (line/bar), urgency distribution, and support type breakdown. All charts render with data reflecting the reports submitted during testing. |  | Not Tested
TC-057 | MOD-10 Analytics | Charts Reflect Live Data After New Submission | Positive | Admin is on /admin/analytics with current chart data visible. | Submit one new report from a different account with County = Kilifi. | 1. In a separate browser tab, sign in as a reporter (non-admin) and submit a new report with County = Kilifi. 2. Return to the admin /admin/analytics tab. 3. Refresh the analytics page. 4. Observe the county chart or data. | After refresh, the Kilifi count in the county chart (or data table) increments to reflect the newly submitted report. Charts are data-driven and reflect real-time database state on page load. |  | Not Tested
TC-058 | MOD-10 Analytics | Map Loads with Incident Markers | Positive | Admin is signed in. At least 2 reports have been submitted with GPS coordinates captured (TC-022 GPS test) or county data. | Reports from earlier test modules. | 1. As admin, navigate to the map view (check admin navigation for 'Map' link). 2. Allow the map to fully load. 3. Observe the markers or pins on the map. | A Kenya map renders successfully. Markers or pins are displayed representing submitted incidents — either at GPS coordinates (if captured) or at county-level centroids. The map is interactive: it can be zoomed with the scroll wheel and panned by dragging. |  | Not Tested
TC-059 | MOD-10 Analytics | Map Pin Click — Popup Shows No PII | Validation | Admin is on the map view. At least one marker is visible. | No specific data — inspect every visible popup. | 1. Click on any map marker/pin. 2. Observe the popup or sidebar that appears. 3. Record every piece of information displayed in the popup. 4. Repeat for all visible markers. | Each popup displays only anonymised data: county name, incident type, date, and urgency level. Under no circumstances is a victim's name, real email address, physical address, phone number, or IP address displayed in any map popup. This is a critical privacy requirement. |  | Not Tested
TC-060 | MOD-10 Analytics | Map Renders on Mobile Viewport | Positive | Admin is signed in. Testing on a mobile device or with browser resized to 375px width. | Mobile device or browser developer tools at 375px width. | 1. Open the map view on a mobile device OR resize the desktop browser to 375px wide using developer tools. 2. Observe the map layout. 3. Attempt to tap a marker. | The map renders full-width on mobile. No horizontal scroll overflow. Markers are visible and tappable with a finger (minimum touch target ~44px). Popups display within the visible screen area without being cut off. |  | Not Tested
TC-061 | MOD-10 Analytics | Analytics Charts Responsive on Mobile | Positive | Admin is signed in. Browser resized to 375px width. | Mobile-width browser viewport. | 1. On /admin/analytics, resize browser to 375px width. 2. Scroll through all charts. 3. Observe chart layout and readability. | All charts reflow to fit the narrow viewport. No chart overflows horizontally. Chart labels and data values remain legible. No chart is completely hidden or inaccessible. |  | Not Tested
MOD-11 — Settings & Language Switcher
TC-062 | MOD-11 Settings | Settings Page — Six Language Options Displayed | Positive | User is signed in (any account type). | No specific data required. | 1. Navigate to /settings. 2. Observe the language selection section. | The settings page loads and displays a grid of six language options: English 🇬🇧, Kiswahili 🇰🇪, Français 🇫🇷, Português 🇧🇷, Deutsch 🇩🇪, العربية 🇸🇦. Each option shows the flag, the native language name, and the English name. The currently active language is highlighted (purple border/background with a check icon). |  | Not Tested
TC-063 | MOD-11 Settings | Select French — All Platform Text Updates to French | Positive | User is on /settings. Current language is English. | Language to select: Français | 1. On /settings, click the 'Français' language card. 2. Observe the immediate reaction on the settings page. 3. Navigate to the landing page (/). 4. Navigate to /report. 5. Navigate to /auth/login. | Step 2: A toast notification appears: 'Français — Language saved.' The settings page text (title, subtitle, auto-detect note) immediately changes to French. Steps 3-5: ALL platform text across landing page, report form labels, field placeholders, button text, and login form is rendered in French. No English text remains except for the brand name 'WHRD Hub'. |  | Not Tested
TC-064 | MOD-11 Settings | Select Arabic — RTL Layout Applied | Positive | User is on /settings. | Language to select: العربية | 1. On /settings, click the 'العربية' language card. 2. Observe the page layout immediately after selection. 3. Navigate to /report and observe the form layout. | Step 2: The page layout changes to right-to-left (RTL). Text is right-aligned. Navigation elements mirror (logo on right, nav links on left, or equivalent mirroring). Step 3: The report form shows Arabic labels only (no secondary English or Swahili). Text inputs, dropdowns, and pill buttons all align to the right side. |  | Not Tested
TC-065 | MOD-11 Settings | Language Persists After Hard Refresh | Validation | User has selected Kiswahili (or any non-English language) on /settings. | Language last selected: Kiswahili | 1. Select 'Kiswahili' on /settings. 2. Hard-refresh the page: press Ctrl + Shift + R (Windows) or Cmd + Shift + R (Mac). 3. Observe the page language after reload. | After a hard refresh, the page reloads in Kiswahili. The language selection is stored in the browser's localStorage. The platform does not revert to English on refresh. The active language card on /settings still shows Kiswahili as selected. |  | Not Tested
TC-066 | MOD-11 Settings | Compact Language Switcher in Navigation Bar | Positive | User is on any page (landing page, /report, or /dashboard). | No specific data required. | 1. Locate the globe icon with a language code (e.g. 'EN') in the navigation bar. 2. Click it. 3. Observe the dropdown. 4. Select a different language from the dropdown. | Step 2-3: A dropdown menu appears listing all 6 languages with their flags and native names. The current language is highlighted. Step 4: Selecting a language from the nav dropdown immediately updates all visible page text without requiring navigation to /settings. The language code in the nav bar updates to reflect the new selection (e.g. 'FR' for Français). |  | Not Tested
TC-067 | MOD-11 Settings | Login Page Includes Language Switcher | Positive | User is on /auth/login. Language is currently set to English. | Language to change: Deutsch | 1. Navigate to /auth/login. 2. Locate the language switcher on the login page. 3. Change the language to Deutsch. 4. Observe the login form content. | The login page includes a language switcher (in the header area of the login card). Changing to Deutsch updates all login form text: title ('Willkommen zurück' or equivalent), field labels, button text ('Anmelden'), and the anonymous user hint. The Google sign-in button also updates its label. |  | Not Tested
MOD-12 — Multilingual Testing (EN/SW/FR/PT/DE/AR)
TC-068 | MOD-12 Multilingual | EN + SW Dual Labels on Report Form | Positive | Platform language is set to English. | Language: English (default or set via /settings) | 1. Set platform language to English. 2. Navigate to /report. 3. Inspect the field labels throughout the form — specifically: 'Tell us what happened', 'County / Region', 'Where did the violence happen?', 'Password'. | When language is English, each field label shows the English label as the primary text, with the Swahili equivalent displayed in smaller, muted text in parentheses. Example: 'Tell us what happened (Tuambie kilichotokea)'. This dual-language display applies to English and Swahili only. |  | Not Tested
TC-069 | MOD-12 Multilingual | SW + EN Dual Labels on Report Form | Positive | Platform language is set to Kiswahili. | Language: Kiswahili (set via /settings or nav switcher) | 1. Set platform language to Kiswahili. 2. Navigate to /report. 3. Inspect the same field labels as TC-068. | When language is Swahili, each field label shows the Swahili label as the primary text, with the English equivalent in smaller, muted text in parentheses. Example: 'Tuambie kilichotokea (Tell us what happened)'. Swahili is the primary language; English is the secondary. |  | Not Tested
TC-070 | MOD-12 Multilingual | FR — Single Labels Only (No Secondary Language) | Validation | Platform language is set to Français. | Language: Français | 1. Set platform language to Français. 2. Navigate to /report. 3. Inspect all field labels. 4. Look specifically for any secondary language text in parentheses. | All field labels are shown in French only. No secondary language (English or Swahili) appears in parentheses. This is the correct behaviour for FR, PT, DE, and AR — dual-language labels only appear in EN and SW modes. |  | Not Tested
TC-071 | MOD-12 Multilingual | Validation Error Messages Translate | Validation | Platform language is set to Kiswahili. User is on /report. | Language: Kiswahili | 1. Set language to Kiswahili. 2. Navigate to /report. 3. Without filling any required fields, click 'Submit report securely' (or equivalent Swahili button label). 4. Observe the inline error messages. | The inline validation errors appear in Swahili, not English. Example: the county error should read in Swahili ('Tafadhali chagua kaunti au mkoa' or equivalent). The button label also shows in Swahili. No English error messages are displayed when the language is set to Swahili. |  | Not Tested
TC-072 | MOD-12 Multilingual | Landing Page Fully Translated — All 6 Languages | Positive | All 6 languages are available in the settings. | Test each language in sequence: EN, SW, FR, PT, DE, AR. | 1. For each language (EN, SW, FR, PT, DE, AR): a. Set the language via /settings or nav switcher. b. Navigate to the landing page (/). c. Check: navigation labels, hero heading and subtitle, 'How it works' section, 'What you can report' list, CTA section, emergency contacts, footer. 2. Record any untranslated (English) text found. | For all 6 languages, the entire landing page renders in the selected language. The sections covered are: nav (Sign in, Dashboard, Report now), hero (title, subtitle, CTA buttons, trust indicators), safety banner, How it works (label, title, subtitle, 3 step cards), What you can report (items), stats, CTA section, emergency strip, and footer. No English text appears in non-English modes (exception: brand name 'WHRD Hub' is acceptable). |  | Not Tested
TC-073 | MOD-12 Multilingual | Success Page Translates After Portuguese Submission | Positive | Platform language set to Português. User has just submitted a report (TC-010 flow). | Language: Português Complete TC-010 steps while language is set to Português. | 1. Set language to Português. 2. Navigate to /report and submit a valid report (Violence type = Online, Description = 30+ chars, County = Nairobi, Password = UATPort2026). 3. Observe the /report/success page. | The /report/success page displays entirely in Portuguese: the 'Report received' heading in Portuguese, all three next-steps in Portuguese, the 'You are already signed in' notice in Portuguese, and both action buttons ('Go to your dashboard', 'Return home') labelled in Portuguese. |  | Not Tested
TC-074 | MOD-12 Multilingual | Language Auto-Detect from Browser Setting | Positive | Browser language setting is changeable in the test environment. LocalStorage key 'whrd-language' is cleared. | Browser set to French (fr-FR) in browser language settings. localStorage cleared. | 1. In browser settings, set the preferred language to French (fr-FR) as the primary language. 2. Clear localStorage (DevTools > Application > LocalStorage > Clear All). 3. Navigate to the staging URL for the first time. 4. Observe the landing page language without having manually selected a language. | The platform auto-detects the browser language and loads in French without any manual selection. This behaviour occurs only when no language preference has been previously saved in localStorage. If localStorage contains a saved preference, that preference takes priority over the browser language. |  | Not Tested
TC-075 | MOD-12 Multilingual | Arabic RTL — Report Form Direction and Usability | Positive | Platform language is set to Arabic (العربية). | Language: Arabic | 1. Set language to Arabic. 2. Navigate to /report. 3. Attempt to fill in each field type: text input, dropdown (county), pill button, checkbox, password field. 4. Submit a valid report. | The report form renders in RTL layout. All text and labels are right-aligned. Input fields accept right-to-left text entry. Dropdown opens correctly. Pill buttons are selectable. Checkboxes work. Password field has show/hide toggle on the correct (left) side in RTL. A valid report can be submitted successfully while in Arabic mode. |  | Not Tested
MOD-13 — Accessibility — Keyboard, Contrast & Screen Reader
TC-076 | MOD-13 Accessibility | Keyboard Tab Navigation — Report Form | Positive | User is on /report. No mouse input — keyboard only for this test. | Keyboard only (Tab, Shift+Tab, Enter, Space). | 1. Navigate to /report using the browser address bar. 2. Without using the mouse, press Tab repeatedly. 3. Observe which elements receive focus and in what order. 4. When focus lands on a pill button, press Enter or Space. 5. When focus lands on the county dropdown, use arrow keys to select 'Nairobi'. | Every interactive element — pills, text inputs, the county dropdown, checkboxes, the file picker button, and the Submit button — receives visible keyboard focus in a logical top-to-bottom, left-to-right order. Pressing Enter/Space on a pill selects it. Arrow keys navigate dropdown options. No interactive element is skipped or inaccessible by keyboard. |  | Not Tested
TC-077 | MOD-13 Accessibility | Focus Ring Visible on All Interactive Elements | Positive | User is on /report (or any page with interactive elements). | No specific data required. | 1. Press Tab on any page to begin keyboard navigation. 2. Observe each focused element as Tab is pressed. 3. Test on: pill buttons, text inputs, dropdowns, checkboxes, the submit button, and navigation links. | Every focused element displays a clearly visible focus ring (purple outline or equivalent). No element receives focus without a visual indicator. The focus ring is distinct enough to be visible on both light and dark backgrounds. Elements do not appear 'invisible focused'. |  | Not Tested
TC-078 | MOD-13 Accessibility | Primary Button Colour Contrast — WCAG AA | Positive | User is on any page containing the primary 'Report now' or 'Submit report securely' button. | Use browser DevTools colour picker or a contrast checker tool (e.g. WebAIM Contrast Checker). | 1. Identify the primary purple button (e.g. 'Report now' or 'Submit report securely'). 2. Using DevTools or a colour picker, note the background colour (purple) and the text colour (white). 3. Input these values into a WCAG contrast checker. | The contrast ratio between white text (#FFFFFF) and the purple button background meets or exceeds 4.5:1, the WCAG 2.1 AA minimum for normal-weight text at 14px. Record the actual contrast ratio in the Actual Result column. |  | Not Tested
TC-079 | MOD-13 Accessibility | Error Messages Accessible to Screen Readers | Positive | User has VoiceOver (Mac) or NVDA (Windows) enabled. User is on /report. | Screen reader software active. | 1. Enable your screen reader (VoiceOver: Cmd+F5 on Mac; NVDA: Ctrl+Alt+N on Windows). 2. Navigate to /report. 3. Press the submit button without filling required fields to trigger validation errors. 4. Listen to what the screen reader announces. | After triggering validation errors, the screen reader announces the error messages — either by reading them automatically (via aria-live region announcement) or by moving focus to the first error field and reading its label and error text. The user is able to understand what went wrong without needing to visually inspect the page. |  | Not Tested
TC-080 | MOD-13 Accessibility | No Horizontal Scroll at 375px Viewport | Positive | Desktop browser with developer tools available. | Browser viewport: 375px wide (iPhone SE simulation in DevTools). | 1. Open DevTools (F12). 2. Enable responsive design mode and set the viewport to 375px wide. 3. Navigate through: landing page, /report (all sections), /auth/login, /dashboard. 4. On each page, check for horizontal scrollbars or content that extends beyond the viewport width. | No horizontal scrollbar appears on any page at 375px viewport width. All content — including pill buttons, cards, tables, and navigation — fits within the 375px width. Text wraps correctly and does not overflow horizontally. |  | Not Tested
TC-081 | MOD-13 Accessibility | Touch Target Sizes — Mobile Usability | Positive | Testing on a physical mobile device (or mobile emulation at 375px). | Mobile device or 375px emulation. | 1. On a mobile device, navigate to /report. 2. Attempt to tap each interactive element: pills, checkboxes, dropdown, submit button, show/hide password toggle. 3. Note any elements that require multiple tap attempts to activate. | All interactive elements are tappable on the first attempt without precision. Pill buttons, checkboxes, and all other touch targets meet the minimum 44×44px touch target size. The show/hide password toggle (eye icon) is reachable without accidental adjacent taps. |  | Not Tested
TC-082 | MOD-13 Accessibility | Pinch-Zoom Not Disabled on Mobile | Positive | Testing on a physical mobile device. | Mobile device with pinch-zoom capability. | 1. On a mobile device, open any page on the platform. 2. Attempt to pinch-zoom the page. 3. Attempt to double-tap to zoom. | Pinch-zoom works. The page scales up when pinched. The viewport meta tag does NOT include 'user-scalable=no' or 'maximum-scale=1' — these would block accessibility-required zoom functionality. Users who need to zoom for readability can do so freely. |  | Not Tested

## SAAS Test Scenarios
WHRD HUB — SAAS COMMUNITY PLATFORM — UAT TEST SCENARIOS
Test ID | Module | Scenario Title | Test Type | Pre-Conditions | Test Data Required | Test Steps (numbered) | Expected Result | Actual Result (Tester fills in) | Status (Pass/Fail/Blocked) | Defect Ref | Tester Name | Date Tested | Comments / Observations
SAAS-01 — Access, Shared Auth & Cross-Platform
SS-001 | SAAS-01 | Landing page loads (split view) | Positive | SAAS staging URL. Desktop Chrome. | No credentials. | 1. Open the SAAS URL. 2. Let the page fully load. 3. Observe layout on desktop. | Landing loads within 5s: official content on the left, the live Community Feed on the right, the full WHRD Hub logo (with 'Protect. Heal. Nurture.'), and the tagline 'A home for Women Human Rights Defenders across Kenya & Beyond'. No console errors. |  | Not Tested
SS-002 | SAAS-01 | Sign in with shared account | Positive | An account created on the reporting platform exists (shared auth DB). | Registered email + password. | 1. Go to the SAAS /login. 2. Enter the email/password used on the reporting platform. 3. Click Sign In. | The same credentials work (shared Supabase auth). User signs in and lands in the SAAS dashboard, not the marketing landing. |  | Not Tested
SS-003 | SAAS-01 | Continue with Google lands inside the SAAS | Positive | Google provider enabled; Supabase redirect URLs include the SAAS callback (wildcard). | A Google account. | 1. On /login click 'Continue with Google'. 2. Pick the Google account. 3. Observe the destination. | After Google auth the user returns to the SAAS and lands in the dashboard (or /onboarding for a new account) — not the landing page. |  | Not Tested
SS-004 | SAAS-01 | Switch to reporting platform | Positive | Signed in on the SAAS. | None. | 1. In the top nav, click 'Reporting'. 2. Observe navigation. | User is taken to the reporting platform dashboard. The session carries over (same auth). |  | Not Tested
SS-005 | SAAS-01 | Admin view toggle persists | Positive | Account has is_hub_admin = true. | Admin account. | 1. Sign in as the admin. 2. Open the profile/user menu; use the Admin view toggle to enter the Hub console. 3. Sign out and sign back in. | The admin can switch between member and admin views. The chosen view persists across sign-out/in on the same device. |  | Not Tested
SAAS-02 — Onboarding (T&C, County, CBO, Femtorship)
SS-006 | SAAS-02 | New user routed to onboarding, T&C first | Validation | Brand-new account; onboarding not completed. | New account. | 1. Sign in / sign up with a new account. 2. Observe the first screen. | User is sent to onboarding before the dashboard. Terms & Conditions are presented first. |  | Not Tested
SS-007 | SAAS-02 | Cannot proceed without accepting T&C | Validation | On onboarding. | None. | 1. Leave the T&C acceptance unchecked. 2. Try to continue. | The continue button stays disabled until the T&C checkbox is ticked. |  | Not Tested
SS-008 | SAAS-02 | County + organization (CBO) capture | Positive | On onboarding. | County: Nairobi. CBO: pick existing or 'Add new'. | 1. Select a county network. 2. Choose an existing CBO or create a new one. 3. Continue. | County and CBO are saved to the profile/membership. Creating a new CBO adds it as pending verification. |  | Not Tested
SS-009 | SAAS-02 | Femtorship questionnaire captured | Positive | On onboarding / profile. | Sample answers to the femtorship questions. | 1. Complete the femtorship questions (leadership, guidance areas, can provide support, etc.). 2. Save. | Answers are stored on the femtorship profile and used later for matching. |  | Not Tested
SS-010 | SAAS-02 | Onboarding not re-triggered | Validation | Onboarding completed once. | Same account. | 1. Sign out. 2. Sign back in. | User goes straight to the dashboard; onboarding is not shown again. |  | Not Tested
SAAS-03 — Landing & Marketing Pages
SS-011 | SAAS-03 | Tagline shows '& Beyond' | Positive | Landing loaded. | None. | 1. Read the hero tagline and footer. | Reads 'A home for Women Human Rights Defenders across Kenya & Beyond' on the landing and footer. |  | Not Tested
SS-012 | SAAS-03 | County Networks page lists 9 | Positive | On the public site. | None. | 1. Open Our Work → County Networks. 2. Count the networks; open one. | Nine county networks are listed; each opens its own page with content (no 404). |  | Not Tested
SS-013 | SAAS-03 | Our Impact section loads | Positive | On the public site. | None. | 1. About Us → Our Impact. | The Impact section opens with key figures and highlights (no dead link, not a repeat of another page). |  | Not Tested
SS-014 | SAAS-03 | Blog list + article + gallery | Positive | At least one published story. | None. | 1. Open Voices → Blog. 2. Open a story. | Blog list renders; the article shows the full body, and any photos load as a gallery after the text. |  | Not Tested
SS-015 | SAAS-03 | Footer, socials and logo | Positive | Any public page. | None. | 1. Scroll to the footer. | Footer shows the full logo, contact details, and working social links. No 'Report Abuse' CTA in the footer. |  | Not Tested
SAAS-04 — Community Feed
SS-016 | SAAS-04 | Feed shows posts + Hub videos | Positive | Feed has approved posts and Hub videos. | None. | 1. Open the Community Feed. 2. Scroll. | Approved posts and Hub YouTube videos appear; pinned items are at the top, then newest first. |  | Not Tested
SS-017 | SAAS-04 | Guest reaction limit + sign-in gate | Validation | Signed out. | None. | 1. As a guest, react/support on posts. 2. Continue past 3 reactions. | Guests can react up to 3 times; the 4th prompts sign-in. The 3 guest reactions sync to the account after signing in. |  | Not Tested
SS-018 | SAAS-04 | Signed-in reaction updates count | Positive | Signed in. | None. | 1. Support a post. 2. Observe the count. | The support/reaction count increments immediately and persists on refresh. |  | Not Tested
SS-019 | SAAS-04 | YouTube link post embeds player | Positive | A post created with a YouTube link. | None. | 1. Open a post that has a YouTube link. | The video renders as an embedded, playable player (not a raw link). |  | Not Tested
SS-020 | SAAS-04 | Reporting entry present | Positive | Any page. | None. | 1. Look for the route back to the reporting platform. | A clear path to the reporting platform is available in the nav/menu. |  | Not Tested
SAAS-05 — Story Authoring (Editor & Workflow)
SS-021 | SAAS-05 | Create post with media | Positive | Signed in. | An image or document under the size limit. | 1. Open the composer. 2. Write an update and attach media. 3. Post. | The post is created; a member's post goes to review, an admin's publishes immediately. |  | Not Tested
SS-022 | SAAS-05 | Write a story with the rich editor | Positive | Signed in. | Sample story text. | 1. Composer → Write a story. 2. Use the toolbar: heading, list, quote, link, image. 3. Preview. | The TipTap editor applies formatting; Preview matches how the story will render. |  | Not Tested
SS-023 | SAAS-05 | Save draft | Positive | Writing a story. | Draft content. | 1. Click 'Save draft'. 2. Go to Profile → My Activity → Stories. | The story is saved as a Draft and appears under activity with an Edit link. |  | Not Tested
SS-024 | SAAS-05 | Submit for review | Positive | A draft or new story. | Story with enough content. | 1. Click 'Submit for review'. | Status becomes 'In review' and the Hub admins are notified. It appears in the admin queue. |  | Not Tested
SS-025 | SAAS-05 | Revise a declined story | Positive | A story that was declined with a note. | Revised content. | 1. Profile → Stories → open the declined story ('Revise'). 2. Read the decline note, edit, resubmit. | The decline note is shown; edits save and resubmitting returns it to 'In review'. |  | Not Tested
SAAS-06 — Hub Admin Console
SS-026 | SAAS-06 | Overview + needs-attention inbox | Positive | Signed in as Hub admin; items pending. | Admin account. | 1. Open the Hub overview. 2. Toggle the inbox between Posts / CBOs / Stories. | KPIs and management cards render; the inbox toggles between pending Posts, CBOs and Stories, each row opening its detail. |  | Not Tested
SS-027 | SAAS-06 | Review, edit & publish | Positive | A pending post/story exists. | None. | 1. Open a pending item. 2. Edit it in the editor. 3. Approve & publish. | Edits save; on publish the item goes live on the feed/blog and the author is notified. |  | Not Tested
SS-028 | SAAS-06 | Decline with note | Positive | A pending item. | Decline reason. | 1. Open the item. 2. Decline with a note. | Item is marked declined, the author is notified with the note, and it shows under the Declined filter. |  | Not Tested
SS-029 | SAAS-06 | Verify a CBO | Positive | A CBO is pending verification. | None. | 1. CBOs → open an unverified CBO. 2. Use the verify action at the top. | The CBO becomes Verified; its members and content can then go public. |  | Not Tested
SS-030 | SAAS-06 | Member drill-down + femtorship | Positive | A member with content/matches. | None. | 1. Members → open a member. 2. Review their content table and femtorship panel. | The member's posts/stories are listed and their femtorship role and matches (mentoring / mentored by) are shown. |  | Not Tested
SS-031 | SAAS-06 | Admin composer: pin + YouTube | Positive | Signed in as admin. | A YouTube link. | 1. Composer → enable 'Pin to top', paste a YouTube link with text. 2. Post. | The admin post auto-publishes, is pinned to the top of the feed, and shows the embedded video. |  | Not Tested
SAAS-07 — Profile, Femtorship & Accessibility
SS-032 | SAAS-07 | Edit profile | Positive | Signed in. | New name/title/bio/county. | 1. Profile → Account. 2. Update fields and save. | Changes save and are reflected across the platform. |  | Not Tested
SS-033 | SAAS-07 | Femtorship form + matches | Positive | Signed in. | Updated answers. | 1. Profile → Femtorship. 2. Update answers; view any connected matches. | Answers save; existing matches are listed, or the form shows if none yet. |  | Not Tested
SS-034 | SAAS-07 | Accessibility controls persist | Positive | Signed in or guest. | None. | 1. Open Accessibility (profile or widget). 2. Change text size / contrast / reduce motion. 3. Reload. | Settings apply immediately and persist on this device after reload. |  | Not Tested
SS-035 | SAAS-07 | Privacy: delete own content / account | Validation | Signed in with own content. | None. | 1. Profile → Privacy & Security. 2. Delete a post/story; review the delete-account option. | Own content is removed; the delete-account flow warns clearly before any irreversible action. |  | Not Tested
SS-036 | SAAS-07 | Activity tabs | Positive | Signed in with activity. | None. | 1. Profile → My Activity. 2. Switch Posts / Stories / Supported. | Each tab lists the user's items with correct status pills; declined/draft stories offer edit. |  | Not Tested

## Defect Log
WHRD HUB UAT — DEFECT LOG
Log ALL defects here immediately. Include the URL, the test case reference, and a screenshot filename where possible. Do not modify a defect entry after logging — add a new row if needed.
Defect ID | Test Case Ref | Module | Defect Title | Severity (Critical/High/ Medium/Low) | Defect Description (What happened vs. what was expected) | Steps to Reproduce | URL at Point of Failure | Screenshot / Evidence Ref | Status (Open/Fixed/ Retested/Closed) | Assigned To (Dev Team) | Date Raised | Date Fixed / Closed
DEF-001 | [8 empty] | Open
DEF-002 | [8 empty] | Open
DEF-003 | [8 empty] | Open
DEF-004 | [8 empty] | Open
DEF-005 | [8 empty] | Open
DEF-006 | [8 empty] | Open
DEF-007 | [8 empty] | Open
DEF-008 | [8 empty] | Open
DEF-009 | [8 empty] | Open
DEF-010 | [8 empty] | Open
DEF-011 | [8 empty] | Open
DEF-012 | [8 empty] | Open
DEF-013 | [8 empty] | Open
DEF-014 | [8 empty] | Open
DEF-015 | [8 empty] | Open
DEF-016 | [8 empty] | Open
DEF-017 | [8 empty] | Open
DEF-018 | [8 empty] | Open
DEF-019 | [8 empty] | Open
DEF-020 | [8 empty] | Open

## UAT Sign-Off Register
WHRD HUB UAT — FORMAL SIGN-OFF REGISTER
Each UAT participant must sign off below ONLY when all scenarios assigned to their role have been executed and the results are recorded. A sign-off certifies that testing is complete and the results are accurate.
Name | Job Title / Role | UAT Role | Modules Tested | Scenarios Passed / Total Assigned | Sign-Off Date | Signature / Initials
Oliver Wainaina | Product Owner / Platform Developer | Test Co-ordinator & Final Reviewer | All Modules (MOD-01 to MOD-13)
| Reporter / WHRD User | Primary Reporter Tester | MOD-01, MOD-02, MOD-03, MOD-04, MOD-07
| Reporter / WHRD User | Anonymous Flow Tester | MOD-02, MOD-03, MOD-04, MOD-11, MOD-12
| Admin / Case Worker | Admin Flow Tester | MOD-08, MOD-09, MOD-10, MOD-01
| Reporter — Google account | Google OAuth Tester | MOD-06, MOD-04, MOD-05, MOD-07
| Reporter — Email account | Email Flow Tester | MOD-05, MOD-04, MOD-07, MOD-13
| Accessibility Tester | A11y & Multilingual | MOD-13, MOD-12, MOD-11
OVERALL UAT SIGN-OFF — PRODUCT OWNER FINAL APPROVAL
UAT Outcome | [ ] PASSED — System approved for use [ ] FAILED — Outstanding critical defects prevent approval [ ] CONDITIONAL — Approved with known minor defects deferred
Outstanding Defects at Close | Critical: _____ High: _____ Medium: _____ Low: _____
Go-Live Recommendation | [ ] Approved for go-live as at [date] [ ] Conditional approval — defects listed above to be resolved within [n] days [ ] Not approved — UAT failed, defects must be resolved and retested
Product Owner Name | Oliver Wainaina
Product Owner Signature
Date of Final Sign-Off
UAT PASS CRITERIA: (1) All CRITICAL test cases pass. (2) ≥ 90% of HIGH test cases pass. (3) All three user flows (Anonymous, Email, Google) complete end-to-end without blocking defects. (4) Admin can view, fact-check, and update case status. (5) Platform usable in English and Swahili. (6) No PII exposed on map or admin list. (7) No horizontal scroll on 375px mobile.